## Slide 1: OE/AAA Update
Construction Safety Phasing Plan Evaluations
Airport Layout Plan Updates
2022 South Dakota Airports Conference
Kyle Sebesta, PE
April 6, 2022

## Slide 2: Outline
CSPP Evaluations
  SOP 1.00, FAA Evaluation of Sponsor’s CSPPs Funded by AIP or PFC
  Temporary construction points of interest
  Reviewer’s view
  New component types
  Determination letters
ALP Updates
  Pen and ink vs. ALP Update

## Slide 3: CSPP Evaluation
https://www.faa.gov/airports/resources/sops/
1 case for CSPP by itself, located at ARP, elevation 1’, height 1’
  Routed for review differently than PT77 points of interest
1 case for each point of interest for airspace review
  Guidance in SOP 1.00
  New codes in 2021, including stationary equipment and mobile equipment

## Slide 4: Temporary Construction Points of Interest
Title 14 CFR Part 77 establishes notice criteria
SOP 1.00 Appendix C, Table C-1 – Guidance for Identifying Objects for Temporary Construction Activity
  Construction area boundary
  Staging area/stockpile areas/batch plants as logical
  Haul route points near active movement areas or runway ends
  Equipment that may impact line of sight
  Items in/near NAVAID critical areas
Program managers are willing to review CSPPs and points of interest prior to OE/AAA submission
  During review of Engineering Design Report may work best

## Slide 5: Reviewer’s View of Submitted Cases
Helpful information to provide to streamline review
  Which point on the plan does the case correspond to?
  Which phase is applicable?
  Detailed case description
  Correct component/structure type
  Enough points to capture needed reviews; not so many that clutter the review process

## Slide 6: New Component Types in OE/AAA System
Structure types added for stationary and mobile equipment
  Can be applicable to project areas, haul routes, stockpile areas, etc.
  “Other Desc” not required, but may be helpful

## Slide 7: Determination Letters
Read and review content of determination letters
  FAA Action
    Approval vs conditional approval
  Conditions of Acceptance
    Range from following AC 150/5370-2 to NOTAMs to various obstruction mitigation requirements
    May include comments from several FAA divisions
  Limitations of FAA Action
  Required Sponsor Actions

## Slide 8: ALP Updates
ALP Update should be completed for projects expected to have significant impact on aeronautical or airport operations
  Submit separate OE/AAA case for ALP update to be reviewed alongside airspace cases
Pen and Ink update should be completed for projects that will not have a significant impact on aeronautical or airport operations
  ADO staff will use airspace case sketch to update their copy of the ALP
Work with FAA program manager to determine appropriate course of action for each project

## Slide 9: Questions?
Kyle Sebesta, PE
Kyle.E.Sebesta@faa.gov
2301 University Dr., Bldg. 23B
Bismarck, ND 58504